## Guide
Costs and Benefits Analysis
Guide to the tool
PURPOSE
This tool is meant for analysing program/project's monetary and qualitative viability.
The tool enables a comparison of three scenarios (options).
The scenario viabilities can be analysed by changing key parameters with sliders (sensitivity analysis).
TOOL STRUCTURE
|  | Summary: |  | The cumulative net benefit table and graphs show how the costs turn into monetary benefits
The tables below the graphs summarize the various costs and benefits under the main headings
The qualitative benefits are summarised to the right of the graphs
|  | Viability comparison: |  | The interest rate for the calculations is determined here
The viability of the options is compared using five different methods (NPV, annuity, payback, IRR, ROI)
The sheet enables the sensitivity analysis of the options
|  | Option 1-3: |  | The costs and benefits of different scenarios are planned in their own sheets
Review years are determined in Option 1 sheet
Also the residual values of the investment in different scenarios are determined in option sheets
The cost calculation for the entire tool can be adjusted by changing the interest rate on the Viability comparison sheet:
However, it is usually advisable to use 0% as the initial assumption for the calculation rate, because usually the costs and future benefits of the program / project are already estimated in current money (present value).
BREAKDOWN OF COSTS AND BENEFITS
This cost-benefit tool is intended for breaking down the financial costs and benefits into four areas:
|  | 1. | Costs during the program / project (investment)
|  | 2. | Post-implementation operational costs as a result of the program / project
|  | 3. | Direct income after implementation as well as the savings generated as a result of the program / project
|  | 4. | Post-implementation financial impact on customer space and public service needs
The tool enables the residual value definition of the investment in the Option sheets:
However, most progrmans / projects leave no residual value that can be be converted into cash. If for example the program / project invests in equipment that can be sold after its service life, it is worth determining its residual value.
COSTS BREAKDOWN PRINCIPLES
The change and cost pursued by the program / project is to be allocated according to the functions of the organizational value chain:
|  | 1. | Primary activities
|  | 2. | Digitalisation and technology
|  | 3. | Other supporting activities
The purpose of this breakdown is to identify which activities of the organization in its overall value chain the program / project will change and how much they will incur change costs as well as new operational costs in the future.
The Option sheets provide this breakdown of costs for both the implementation costs and post-implementation cost of the program / project.
BENEFITS BREAKDOWN PRINCIPLES
Similarly, the pursued financial benefit is to be allocated to:
|  | 1. | Direct financial income
|  | 2. | Operational benefits in primary services
|  | 3. | Operational benefits in digitalisation and technology functions
|  | 4. | Operational benefits in other supporting functions
|  | 5. | Impact to the need for public services
|  | 6. | Impacts in different customer groups of the local government
Qualitative benefits and associated risks are also described in the Option sheets:
|  | 1. | Five most important non-monetary benefits that a program / project produces
|  | 2. | Other additional benefits that cannot be measured in money, but are not crucially important either.
In addition, more detailed calculations can attached:
|  | 1. | Each cost-benefit row has a cell in which you can write a reference to a more detailed calculation.
VIABILITY COMPARISON PRINCIPLES AND ITS FUNCTIONALITY
The viability of the options is examined on the Viability comparison sheet using:
|  | 1. | Net present value (NPV)
|  | 2. | Annuity method
|  | 3. | Payback time
|  | 4. | Internal rate of return (IRR)
|  | 5. | Return on investment (ROI)
The sheet automatically marks the most viable option indicated by each method.
The sheet also colors unprofitable options with a red background color.
The sheet allows you to adjust the initial calculation interest rate used in converting future values to present value.
Viability can be analysed by adjusting the parameters with the sliders on the Viability comparison sheet (sensitivity analysis):
|  | 1. | Calculation interest rate
|  | 2. | Total cost of investment
|  | 3. | Useful lifetime of the investment
|  | 4. | Average annual operating cost
|  | 5. | Average annual monetary benefits
|  | 6. | Residual value
Sensitivity analysis sliders do not affect the original values on the Summary sheet and the Option sheets.
Primary activities
Value chains of the divisions and public utilities that provide the city's services to for example to residents, companies, communities and tourists.
Supply
Service operations and logistics
Service offering
Delivery and support
Digitalisation and technology
Improving primary and support functions through digital and technological means
Supporting activities
The supporting functions required for maintaining the primary activities: E.g. finance and treasury, strategy, general administration and HR
Value

## Summary
Cost-benefit summary of the options
[This sheet summarizes the implementation cost of the program / project, the running costs, the financial benefits / savings, and the financial customer and ecosystem impacts between the different options. The sheet also indicates the payback period, ie when the break-even point is reached (as cash flow and with depreciation separately). The sheet discounts the values entered on the Option sheet to the present value. The discount rate is determined on the Profitability comparison sheet.]
Accumulative net benefit in different options | [11 empty] | Key qualitative benefits in different options
Discounted with 0% discount rate.
In cash flow [EUR] | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 |  |  | Benefit name | Benefit description
Option 1 | -2 | -8 | -8 | -6 | -5 | -4 | -3 | -2 | -1 | 0 | 1 | Option 1 | 1
Option 2 | -2 | -8 | -7.5 | -5 | -3.5 | -2 | -0.5 | 1 | 2.5 | 4 | 5.5 |  | 2
Option 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3
Using depreciation [EUR] | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 |  | 4
Option 1 | -2 | -5 | -6 | -5 | -5 | -4 | -3 | -2 | -1 | 0 | 1 |  | 5
Option 2 | -2 | -5 | -5.5 | -4 | -3.5 | -2 | -0.5 | 1 | 2.5 | 4 | 5.5
Option 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Benefit name | Benefit description
[12 empty] | Option 2 | 1
2
3
4
5
[14 empty] | Benefit name | Benefit description
[12 empty] | Option 3 | 1
2
3
4
5
Summary of the financial costs and benefits in the different options
Discounted with 0% discount rate.
Vuosi | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032
Program / project investments as cash flow [EUR/a]
Option 1 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 2 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Program / projects investments using depreciation [EUR/a]
Option 1 | 2 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Option 2 | 2 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Option 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Post-implementation costs [EUR/a]
Option 1 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Option 2 | 0 | 0 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5
Option 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Monetary savings and benefits resulted by the program / project [EUR/a]
Option 1 | 0 | 0 | 4 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Option 2 | 0 | 0 | 4 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Option 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Monetary public sector and customer space impacts resulted by the program / projects [EUR/a]
Option 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Option 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Net benefit summary
In cash flow [EUR/a] | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032
Option 1 | -2 | -6 | 0 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Option 2 | -2 | -6 | 0.5 | 2.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
Option 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Using depreciation [EUR/a]
Option 1 | -2 | -3 | -1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1
Option 2 | -2 | -3 | -0.5 | 1.5 | 0.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
Option 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Viability comparison
Viability comparisons of the options
[The option is viable if the present values of the net returns are greater than the investment. In the annuity method, the current acquisition cost is divided into equal annual capital costs, ie annuities, to the holding period. The option is viable when the annual net return is equal to the cost of managing the capital. If the investment has a residual value, its present value must be deducted from the acquisition cost. The comparisons below also deduct annual operating costs from annual monetary benefits. The investment is not discounted in the ROI calculation below.]
Initial values
| Calculation interest rate | 0%
|  | Option 1 | Option 2 | -
| Investment | 8 | 8 | -
| Investment holding period | 9 | 9 | -
| Annual operating cost (avg.) | 3.2727 | 2.8636 | -
| Annual monetary benefits (avg.) | 4.0909 | 4.0909 | -
| Residual value | 0 | 0 | -
Sensitivity analysis
Change the parameters with the sliders
| Calculation interest rate | 0% |  |  | 0% | 30
|  | Option 1 | Option 2 | -
| Investment | 8 | 8 | - | 0% | 100
| Investment holding period | 9 | 9 | - | 0 | 100
| Annual operating cost (avg.) | 3.2727 | 2.8636 | - | 0% | 100
| Annual monetary benefits (avg.) | 4.0909 | 4.0909 | - | 0% | 100
| Residual value | 0 | 0 | - | 0% | 100
NET PRESENT VALUE INDICATES VIABILITY IF IT IS POSITIVE
|  | Option 1 | Option 2 | -
| Sum of net benefits present values | 7.3636 | 11.0455 | -
| Viability (NPV) | -0.63636 | 3.0455 | -
ANNUITY INDICATES VIABILITY IF IT IS LESS THAN ANNUAL INCOME/BENEFIT
|  | Option 1 | Option 2 | -
| Investment annuity | 0.88889 | 0.88889 | -
| All annual net benefits | 0.81818 | 1.2273 | -
| Viability (annuity) | -0.070707 | 0.33838 | -
PAYBACK TIME, INTERNAL RATE OF RETURN AND RETURN ON INVESTMENT
|  | Option 1 | Option 2 | -
| Payback time (with avg. net benefits) | 9.7778 | 6.5185 | -
| Internal rate of return (IRR) | 2.248% | 10.99% | -
| Discounted return on investment (disc ROI) | 10.23% | 15.34% | -
| Suurin nettonykyarvo | 3.0455 | 3.0455 | 3.0455
| Suurin annuiteetti | 0.33838 | 0.33838 | 0.33838
| Pienin takaisinmaksuaika (1) | 6.5185 | 6.5185 | 6.5185
| Suurin IRR (1) | 0.10989 | 0.10989 | 0.10989
| Suurin ROI (1) | 0.15341 | 0.15341 | 0.15341

## Option 1
TRUE
Costs-benefits breakdown: Option 1
[Break down the monetary costs into key groups for both the implementation and post-implementation of program / project. Break down the direct financial savings generated during post-implementation operation into groups similar to the cost breakdown of the program / project. Also assess the indirect monetary benefits in primary services, if any. In addition, assess the indirect financial impact on customers' operations or on the customer base as a whole or on the use of the city's services as a whole. Use the table breakdown for reference. Edit the cost/benefit titles as needed, but do not add or change rows.]
| INVESTMENT COSTS |  |  | TOT | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | Source data | QUALITATIVE BENEFITS
TRUE | Investments in cash flow [EUR/a] | [14 empty] | (sources and assumptions) | Primary benefits
| 0 | Primary activies costs | [15 empty] | Benefit name | Benefit description
|  |  | Consulting costs in primary activities | 0 | [12 empty] | 1
|  |  | Purchase of equipment and materials | 0 | [12 empty] | 2
|  |  | Other purchase | 0 | [12 empty] | 3
| 1 | Digital and tech activities costs | [14 empty] | 4
|  |  | Cyber security | 0 | [12 empty] | 5
|  |  | Digital infrastucture (network, data center, Iaas, PaaS) | 0 | [12 empty] | Additional benefits |  | Benefit description
|  |  | Digital work environment (workstation, printing, phone) | 0 | [12 empty] | 6
|  |  | Other digital equipment | 0 | [12 empty] | 7
|  |  | Digitaaliset applications and software (information systems, developer tools) | 3 | 2023: 3 |  | 8
|  |  | Software development (consulting, …) | 2 | [12 empty] | 9 | bar: 2022 to 2023
| 1 | Supportive and deployment costs
|  |  | Service desk and other similar supporting costs | 0 | [12 empty] | RISKS
|  |  | Learning and education | 1 | [12 empty] | Primary risks | bar: 2023
|  |  | Administrative costs (e.g. project management) | 2 | [13 empty] | Risk name | Risk description | bar: 2022 to 2023
|  | Investments summary (INV cashflow) |  | 8 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1
|  |  | Discounted | 8 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2
3
|  | Residual value (present value) |  | 0 | [12 empty] | 4
5
[17 empty] | Additional risks |  | Risk description
TRUE | Investments using depreciation [EUR/a] | [15 empty] | 6
| 0 | Primary activies costs | [14 empty] | 7
|  |  | Consulting costs in primary activities | 0 | [12 empty] | 8
|  |  | Purchase of equipment and materials | 0 | [12 empty] | 9
|  |  | Other purchase | 0
| 1 | Digital and tech activities costs
|  |  | Cyber security | 0
|  |  | Digital infrastucture (network, data center, Iaas, PaaS) | 0
|  |  | Digital work environment (workstation, printing, phone) | 0
|  |  | Other digital equipment | 0
|  |  | Digitaaliset applications and software (information systems, developer tools) | 3 | bar: 2024 to 2026
|  |  | Software development (consulting, …) | 2 | bar: 2022 to 2023
| 1 | Supportive and deployment costs
|  |  | Service desk and other similar supporting costs | 0
|  |  | Learning and education | 1 | bar: 2023
|  |  | Administrative costs (e.g. project management) | 2 | bar: 2022 to 2023
|  | Investments summary (INV depreciated) |  | 8 | 2 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Discounted | 8 | 2 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | Residual value (present value) |  | 0
TRUE
Use costs [EUR/a]
| 0 | Primary activities use costs
|  |  | Personnel and overhead costs in primary activities | 0
|  |  | Annual material and equipment costs in primary activities (due to investment) | 0
|  |  | Post-implementation consulting in primary activities | 0
| 1 | Digital and tech capability use costs
|  |  | Personnel and overhead costs in digital activities | 0
|  |  | Cyber security use costs | 0
|  |  | Digital infrastructure use costs | 0
|  |  | Digital workding environment use costs | 0
|  |  | Other digital equipment use costs | 0
|  |  | Digital applications and software use costs (maintenance licenses, rent, etc.) | 9 | bar: 2024 to 2032
|  |  | Digital app. and SW running development (consulting) | 9 | bar: 2024 to 2032
| 1 | Supportive use costs
|  |  | Service desk and other similar supporting costs | 9 | bar: 2024 to 2032
|  |  | Learning and education | 9 | bar: 2024 to 2032
|  |  | Other personnel and overhead costs | 0
|  | Use costs summary (USE) |  | 36 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
|  |  | Diskontatut käyttökulut | 36 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
|  |  | Diskontatut käyttökulut korjatulla laskentakorkokannalla | 36 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| Change costs summary in cash flow |  |  | 44 | 2 | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| Change costs summary using depreciations |  |  | 8 | 2 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
TRUE
Income and other monetary benefits [EUR/a]
| 0 | Direct income
|  |  | Revenue | 0
|  |  | Rental income | 0
|  |  | Service payments | 0
|  |  | Other income | 0
| 1 | Operating savings
|  |  | Personnel and overhead savings in primary activities | 27 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
|  |  | Savings on material procurement in primary activities | 0
|  |  | Consulting savings in primary activities | 0
| 1 | Operating process efficiency assumptions
|  |  | Operating unit cost savings (total) | 0
|  |  | Error and change management savings | 1 | bar: 2025
|  |  | Savings in customer journey | 0
| 1 | Operational savings in digital and tech activities
|  |  | Personnel and overhead savings in digital activities | 0
|  |  | Digital infrastructure savings (network, data center, Iaas, PaaS) | 0
|  |  | Digital work environment savings (workstation, printing, phone) | 0
|  |  | Other digital equipment savings | 0
|  |  | Retiring digital appl. and SW maintenance cost savings (maintenance licenses, rent, etc.) | 8 | bar: 2025 to 2032
0
|  |  | Retiring digital applications and SW running development costs | 9 | bar: 2024 to 2032
| 0 | Digital and tech capability efficiency assumptions
|  |  | Unit cost savings in digital service processes (total) | 0
|  |  | Error and change management savings in digital service processes | 0
|  |  | Savings in digital customer journey | 0
| 0 | Other supporting activities savings
|  |  | Personnel and overhead savings in other supporting activities | 0
|  |  | Savings in learning and education | 0
|  | Benefits and income summary |  | 45 | 0 | 0 | 4 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5
|  |  | Discounted | 45 | 0 | 0 | 4 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5
FALSE
Monetary customer impact [EUR/a]
| 0 | Impacts in public service need (savings)
|  |  | City of Helsinki services | 0
|  |  | Other public services | 0
| 0 | Impacts in labor market
|  |  | In Helsinki | 0
|  |  | In the rest of capital area | 0
|  |  | In the rest of Finland | 0
| 0 | Impacts in business environment
|  |  | In Helsinki | 0
|  |  | In the rest of capital area | 0
|  |  | In the rest of Finland | 0
| 0 | Impacts in tourism
|  |  | In Helsinki | 0
|  |  | In the rest of capital area | 0
|  |  | In the rest of Finland | 0
|  | Impacts summary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Discounted | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Income and other monetary benefits total |  |  | 45 | 0 | 0 | 4 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Discounted with initial calculation interest rate |  |  | 45 | 0 | 0 | 4 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Discounted with analysed calculation interest rate |  |  | 45 | 0 | 0 | 4 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Benefits - use costs |  |  |  | 0 | 0 | 0 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Discounted with initial calculation interest rate |  |  |  | 0 | 0 | 0 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Discounted with analysed calculation interest rate |  |  |  | 0 | 0 | 0 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Monetary cost-benefit total |  |  |  | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032
| Accumulative cost-benefit in cash flow (and break-even) |  |  |  | -2 | -8 | -8 | -6 | -5 | -4 | -3 | -2 | -1 | 0 | 1
| Annual cost-benefit |  |  |  | -2 | -6 | 0 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Accumulative cost-benefit using depreciation (and break-even) |  |  |  | -2 | -5 | -2 | 3 | 7 | 12 | 17 | 22 | 27 | 32 | 37
| Annual cost-benefit |  |  |  | -2 | -3 | 3 | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 5
| Monetary cost-benefit total (present value) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Accumulative cost-benefit in cash flow (and break-even) |  |  |  | -2 | -8 | -8 | -6 | -5 | -4 | -3 | -2 | -1 | 0 | 1
| With initial assumptions |  |  |  | -2 | -6 | 0 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Accumulative cost-benefit in cash flow (and break-even) |  |  |  | -2 | -8 | -8 | -6 | -5 | -4 | -3 | -2 | -1 | 0 | 1
| With analysed parameters |  |  |  | -2 | -6 | 0 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Option 2
TRUE
Costs-benefits breakdown: Option 2
[Break down the monetary costs into key groups for both the implementation and post-implementation of program / project. Break down the direct financial savings generated during post-implementation operation into groups similar to the cost breakdown of the program / project. Also assess the indirect monetary benefits in primary services, if any. In addition, assess the indirect financial impact on customers' operations or on the customer base as a whole or on the use of the city's services as a whole. Use the table breakdown for reference. Edit the cost/benefit titles as needed, but do not add or change rows.]
| INVESTMENT COSTS |  |  | TOT | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | Source data | QUALITATIVE BENEFITS
TRUE | Investments in cash flow [EUR/a] | [14 empty] | (sources and assumptions) | Primary benefits
| 0 | Primary activies costs | [15 empty] | Benefit name | Benefit description
|  |  | Consulting costs in primary activities | 0 | [12 empty] | 1
|  |  | Purchase of equipment and materials | 0 | [12 empty] | 2
|  |  | Other purchase | 0 | [12 empty] | 3
| 1 | Digital and tech activities costs | [14 empty] | 4
|  |  | Cyber security | 0 | [12 empty] | 5
|  |  | Digital infrastucture (network, data center, Iaas, PaaS) | 0 | [12 empty] | Additional benefits |  | Benefit description
|  |  | Digital work environment (workstation, printing, phone) | 0 | [12 empty] | 6
|  |  | Other digital equipment | 0 | [12 empty] | 7
|  |  | Digitaaliset applications and software (information systems, developer tools) | 3 | 2023: 3 |  | 8
|  |  | Software development (consulting, …) | 2 | [12 empty] | 9 | bar: 2022 to 2023
| 1 | Supportive and deployment costs
|  |  | Service desk and other similar supporting costs | 0 | [12 empty] | RISKS
|  |  | Learning and education | 1 | [12 empty] | Primary risks | bar: 2023
|  |  | Administrative costs (e.g. project management) | 2 | [13 empty] | Risk name | Risk description | bar: 2022 to 2023
|  | Investments summary (INV cashflow) |  | 8 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1
|  |  | Discounted | 8 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2
3
|  | Residual value (present value) |  | 0 | [12 empty] | 4
5
[17 empty] | Additional risks |  | Risk description
TRUE | Investments using depreciation [EUR/a] | [15 empty] | 6
| 0 | Primary activies costs | [14 empty] | 7
|  |  | Consulting costs in primary activities | 0 | [12 empty] | 8
|  |  | Purchase of equipment and materials | 0 | [12 empty] | 9
|  |  | Other purchase | 0
| 1 | Digital and tech activities costs
|  |  | Cyber security | 0
|  |  | Digital infrastucture (network, data center, Iaas, PaaS) | 0
|  |  | Digital work environment (workstation, printing, phone) | 0
|  |  | Other digital equipment | 0
|  |  | Digitaaliset applications and software (information systems, developer tools) | 3 | bar: 2024 to 2026
|  |  | Software development (consulting, …) | 2 | bar: 2022 to 2023
| 1 | Supportive and deployment costs
|  |  | Service desk and other similar supporting costs | 0
|  |  | Learning and education | 1 | bar: 2023
|  |  | Administrative costs (e.g. project management) | 2 | bar: 2022 to 2023
|  | Investments summary (INV depreciated) |  | 8 | 2 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Discounted | 8 | 2 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | Residual value (present value) |  | 0
TRUE
Use costs [EUR/a]
| 0 | Primary activities use costs
|  |  | Personnel and overhead costs in primary activities | 0
|  |  | Annual material and equipment costs in primary activities (due to investment) | 0
|  |  | Post-implementation consulting in primary activities | 0
| 1 | Digital and tech capability use costs
|  |  | Personnel and overhead costs in digital activities | 0
|  |  | Cyber security use costs | 0
|  |  | Digital infrastructure use costs | 0
|  |  | Digital workding environment use costs | 0
|  |  | Other digital equipment use costs | 0
|  |  | Digital applications and software use costs (maintenance licenses, rent, etc.) | 4.5 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  |  | Digital app. and SW running development (consulting) | 9 | bar: 2024 to 2032
| 1 | Supportive use costs
|  |  | Service desk and other similar supporting costs | 9 | bar: 2024 to 2032
|  |  | Learning and education | 9 | bar: 2024 to 2032
|  |  | Other personnel and overhead costs | 0
|  | Use costs summary (USE) |  | 31.5 | 0 | 0 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5
|  |  | Diskontatut käyttökulut | 31.5 | 0 | 0 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5
|  |  | Diskontatut käyttökulut korjatulla laskentakorkokannalla | 31.5 | 0 | 0 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5
| Change costs summary in cash flow |  |  | 39.5 | 2 | 6 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5
| Change costs summary using depreciations |  |  | 8 | 2 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
TRUE
Income and other monetary benefits [EUR/a]
| 0 | Direct income
|  |  | Revenue | 0
|  |  | Rental income | 0
|  |  | Service payments | 0
|  |  | Other income | 0
| 1 | Operating savings
|  |  | Personnel and overhead savings in primary activities | 27 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
|  |  | Savings on material procurement in primary activities | 0
|  |  | Consulting savings in primary activities | 0
| 1 | Operating process efficiency assumptions
|  |  | Operating unit cost savings (total) | 0
|  |  | Error and change management savings | 1 | bar: 2025
|  |  | Savings in customer journey | 0
| 1 | Operational savings in digital and tech activities
|  |  | Personnel and overhead savings in digital activities | 0
|  |  | Digital infrastructure savings (network, data center, Iaas, PaaS) | 0
|  |  | Digital work environment savings (workstation, printing, phone) | 0
|  |  | Other digital equipment savings | 0
|  |  | Retiring digital appl. and SW maintenance cost savings (maintenance licenses, rent, etc.) | 8 | bar: 2025 to 2032
0
|  |  | Retiring digital applications and SW running development costs | 9 | bar: 2024 to 2032
| 0 | Digital and tech capability efficiency assumptions
|  |  | Unit cost savings in digital service processes (total) | 0
|  |  | Error and change management savings in digital service processes | 0
|  |  | Savings in digital customer journey | 0
| 0 | Other supporting activities savings
|  |  | Personnel and overhead savings in other supporting activities | 0
|  |  | Savings in learning and education | 0
|  | Benefits and income summary |  | 45 | 0 | 0 | 4 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5
|  |  | Discounted | 45 | 0 | 0 | 4 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5
FALSE
Monetary customer impact [EUR/a]
| 0 | Impacts in public service need (savings)
|  |  | City of Helsinki services | 0
|  |  | Other public services | 0
| 0 | Impacts in labor market
|  |  | In Helsinki | 0
|  |  | In the rest of capital area | 0
|  |  | In the rest of Finland | 0
| 0 | Impacts in business environment
|  |  | In Helsinki | 0
|  |  | In the rest of capital area | 0
|  |  | In the rest of Finland | 0
| 0 | Impacts in tourism
|  |  | In Helsinki | 0
|  |  | In the rest of capital area | 0
|  |  | In the rest of Finland | 0
|  | Impacts summary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Discounted | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Income and other monetary benefits total |  |  | 45 | 0 | 0 | 4 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Discounted with initial calculation interest rate |  |  | 45 | 0 | 0 | 4 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Discounted with analysed calculation interest rate |  |  | 45 | 0 | 0 | 4 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Benefits - use costs |  |  |  | 0 | 0 | 0.5 | 2.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
| Discounted with initial calculation interest rate |  |  |  | 0 | 0 | 0.5 | 2.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
| Discounted with analysed calculation interest rate |  |  |  | 0 | 0 | 0.5 | 2.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
| Monetary cost-benefit total |  |  |  | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032
| Accumulative cost-benefit in cash flow (and break-even) |  |  |  | -2 | -8 | -7.5 | -5 | -3.5 | -2 | -0.5 | 1 | 2.5 | 4 | 5.5
| Annual cost-benefit |  |  | 5.5 | -2 | -6 | 0.5 | 2.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
| Accumulative cost-benefit using depreciation (and break-even) |  |  |  | -2 | -5 | -2 | 3 | 7 | 12 | 17 | 22 | 27 | 32 | 37
| Annual cost-benefit |  |  | 37 | -2 | -3 | 3 | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 5
| Monetary cost-benefit total (present value) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Accumulative cost-benefit in cash flow (and break-even) |  |  |  | -2 | -8 | -7.5 | -5 | -3.5 | -2 | -0.5 | 1 | 2.5 | 4 | 5.5
| With initial assumptions |  |  | 5.5 | -2 | -6 | 0.5 | 2.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
| Accumulative cost-benefit in cash flow (and break-even) |  |  |  | -2 | -8 | -7.5 | -5 | -3.5 | -2 | -0.5 | 1 | 2.5 | 4 | 5.5
| With analysed parameters |  |  | 5.5 | -2 | -6 | 0.5 | 2.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5

## Option 3
FALSE
Costs-benefits breakdown: Option 3
[Break down the monetary costs into key groups for both the implementation and post-implementation of program / project. Break down the direct financial savings generated during post-implementation operation into groups similar to the cost breakdown of the program / project. Also assess the indirect monetary benefits in primary services, if any. In addition, assess the indirect financial impact on customers' operations or on the customer base as a whole or on the use of the city's services as a whole. Use the table breakdown for reference. Edit the cost/benefit titles as needed, but do not add or change rows.]
| INVESTMENT COSTS |  |  | TOT | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | Source data | QUALITATIVE BENEFITS
FALSE | Investments in cash flow [EUR/a] | [14 empty] | (sources and assumptions) | Primary benefits
| 0 | Primary activies costs | [15 empty] | Benefit name | Benefit description
|  |  | Consulting costs in primary activities | 0 | [12 empty] | 1
|  |  | Purchase of equipment and materials | 0 | [12 empty] | 2
|  |  | Other purchase | 0 | [12 empty] | 3
| 0 | Digital and tech activities costs | [14 empty] | 4
|  |  | Cyber security | 0 | [12 empty] | 5
|  |  | Digital infrastucture (network, data center, Iaas, PaaS) | 0 | [12 empty] | Additional benefits |  | Benefit description
|  |  | Digital work environment (workstation, printing, phone) | 0 | [12 empty] | 6
|  |  | Other digital equipment | 0 | [12 empty] | 7
|  |  | Digitaaliset applications and software (information systems, developer tools) | 0 | [12 empty] | 8
|  |  | Software development (consulting, …) | 0 | [12 empty] | 9
| 0 | Supportive and deployment costs
|  |  | Service desk and other similar supporting costs | 0 | [12 empty] | RISKS
|  |  | Learning and education | 0 | [12 empty] | Primary risks
|  |  | Administrative costs (e.g. project management) | 0 | [13 empty] | Risk name | Risk description
|  | Investments summary (INV cashflow) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1
|  |  | Discounted | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2
3
|  | Residual value (present value) |  | 0 | [12 empty] | 4
5
[17 empty] | Additional risks |  | Risk description
FALSE | Investments using depreciation [EUR/a] | [15 empty] | 6
| 0 | Primary activies costs | [14 empty] | 7
|  |  | Consulting costs in primary activities | 0 | [12 empty] | 8
|  |  | Purchase of equipment and materials | 0 | [12 empty] | 9
|  |  | Other purchase | 0
| 0 | Digital and tech activities costs
|  |  | Cyber security | 0
|  |  | Digital infrastucture (network, data center, Iaas, PaaS) | 0
|  |  | Digital work environment (workstation, printing, phone) | 0
|  |  | Other digital equipment | 0
|  |  | Digitaaliset applications and software (information systems, developer tools) | 0
|  |  | Software development (consulting, …) | 0
| 0 | Supportive and deployment costs
|  |  | Service desk and other similar supporting costs | 0
|  |  | Learning and education | 0
|  |  | Administrative costs (e.g. project management) | 0
|  | Investments summary (INV depreciated) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Discounted | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Residual value (present value) |  | 0
FALSE
Use costs [EUR/a]
| 0 | Primary activities use costs
|  |  | Personnel and overhead costs in primary activities | 0
|  |  | Annual material and equipment costs in primary activities (due to investment) | 0
|  |  | Post-implementation consulting in primary activities | 0
| 0 | Digital and tech capability use costs
|  |  | Personnel and overhead costs in digital activities | 0
|  |  | Cyber security use costs | 0
|  |  | Digital infrastructure use costs | 0
|  |  | Digital workding environment use costs | 0
|  |  | Other digital equipment use costs | 0
|  |  | Digital applications and software use costs (maintenance licenses, rent, etc.) | 0
|  |  | Digital app. and SW running development (consulting) | 0
| 0 | Supportive use costs
|  |  | Service desk and other similar supporting costs | 0
|  |  | Learning and education | 0
|  |  | Other personnel and overhead costs | 0
|  | Use costs summary (USE) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Diskontatut käyttökulut | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Diskontatut käyttökulut korjatulla laskentakorkokannalla | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Change costs summary in cash flow |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Change costs summary using depreciations |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE
Income and other monetary benefits [EUR/a]
| 0 | Direct income
|  |  | Revenue | 0
|  |  | Rental income | 0
|  |  | Service payments | 0
|  |  | Other income | 0
| 0 | Operating savings
|  |  | Personnel and overhead savings in primary activities | 0
|  |  | Savings on material procurement in primary activities | 0
|  |  | Consulting savings in primary activities | 0
| 0 | Operating process efficiency assumptions
|  |  | Operating unit cost savings (total) | 0
|  |  | Error and change management savings | 0
|  |  | Savings in customer journey | 0
| 0 | Operational savings in digital and tech activities
|  |  | Personnel and overhead savings in digital activities | 0
|  |  | Digital infrastructure savings (network, data center, Iaas, PaaS) | 0
|  |  | Digital work environment savings (workstation, printing, phone) | 0
|  |  | Other digital equipment savings | 0
|  |  | Retiring digital appl. and SW maintenance cost savings (maintenance licenses, rent, etc.) | 0
0
|  |  | Retiring digital applications and SW running development costs | 0
| 0 | Digital and tech capability efficiency assumptions
|  |  | Unit cost savings in digital service processes (total) | 0
|  |  | Error and change management savings in digital service processes | 0
|  |  | Savings in digital customer journey | 0
| 0 | Other supporting activities savings
|  |  | Personnel and overhead savings in other supporting activities | 0
|  |  | Savings in learning and education | 0
|  | Benefits and income summary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Discounted | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE
Monetary customer impact [EUR/a]
| 0 | Impacts in public service need (savings)
|  |  | City of Helsinki services | 0
|  |  | Other public services | 0
| 0 | Impacts in labor market
|  |  | In Helsinki | 0
|  |  | In the rest of capital area | 0
|  |  | In the rest of Finland | 0
| 0 | Impacts in business environment
|  |  | In Helsinki | 0
|  |  | In the rest of capital area | 0
|  |  | In the rest of Finland | 0
| 0 | Impacts in tourism
|  |  | In Helsinki | 0
|  |  | In the rest of capital area | 0
|  |  | In the rest of Finland | 0
|  | Impacts summary |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Discounted | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Income and other monetary benefits total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Discounted with initial calculation interest rate |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Discounted with analysed calculation interest rate |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Benefits - use costs |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Discounted with initial calculation interest rate |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Discounted with analysed calculation interest rate |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Monetary cost-benefit total |  |  |  | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032
| Accumulative cost-benefit in cash flow (and break-even) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Annual cost-benefit |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Accumulative cost-benefit using depreciation (and break-even) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Annual cost-benefit |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Monetary cost-benefit total (present value) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Accumulative cost-benefit in cash flow (and break-even) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| With initial assumptions |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Accumulative cost-benefit in cash flow (and break-even) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| With analysed parameters |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0